PRODUCT REQUIREMENTS DOCUMENT

NoteFlow

A Lightweight Cross-Platform Notes & Productivity App

| Version | 1.0 |
| --- | --- |
| Date | March 1, 2026 |
| Status | Draft |
| Author | Product Team |
| Confidentiality | Internal |

# Table of Contents

# 1. Executive Summary

NoteFlow is a lightweight, cross-platform notes and productivity application designed for individuals and small teams who need a single, unified tool for capturing thoughts, organizing information, and managing tasks. It runs on web, mobile (iOS & Android), and desktop (macOS, Windows, Linux) with real-time sync across all devices.

The product addresses a common pain point: existing note-taking apps are either too simple (lacking task management and voice features) or too bloated (slow, complex, expensive). NoteFlow occupies the sweet spot — powerful enough for daily professional use, yet fast and intuitive enough to replace a sticky note.

## 1.1 Key Value Propositions

- Speed & simplicity: Sub-second app launch, zero-friction note creation.

- Cross-platform sync: Seamless experience across web, mobile, and desktop with offline support.

- Rich organization: Folders, tags, search, filtering, and sorting to manage hundreds of notes effortlessly.

- Built-in productivity: Rich-text editing, to-do lists, task management, and voice transcription in one place.

- AI-powered voice: Transcribe voice inputs and generate summaries of meetings or lectures.

- Extensible: Future integrations with Google Calendar, Teams, Jira, Slack, and more.

# 2. Problem Statement

Knowledge workers, students, and professionals juggle multiple tools for note-taking, task management, and meeting notes. This fragmentation leads to lost context, duplicated effort, and reduced productivity. Specifically:

- Notes are scattered across apps (Apple Notes, Google Keep, Notion, Evernote) with no unified search.

- Meeting recordings require separate transcription tools, and summaries are created manually.

- Task management lives in a different app, disconnected from the notes where tasks originate.

- Switching between platforms (phone to laptop) often means waiting for sync or losing offline edits.

Target Users: Knowledge workers, students, freelancers, and small teams (1–20 people) who take 5+ notes per week and need to manage tasks alongside their notes.

# 3. Goals & Success Metrics

| Goal | Metric | Target (6 months) |
| --- | --- | --- |
| Rapid adoption | Monthly Active Users (MAU) | 50,000 MAU |
| Daily engagement | DAU/MAU ratio | ≥ 40% |
| User retention | D30 retention rate | ≥ 35% |
| Note volume | Avg. notes per active user/week | ≥ 5 |
| Cross-platform usage | % users on 2+ platforms | ≥ 30% |
| Voice feature adoption | % MAU using transcription | ≥ 15% |
| App performance | Cold start time | < 1.5s on all platforms |

# 4. User Personas

## 4.1 Alex — The Busy Professional

Role: Product manager at a tech company. Takes 10–15 notes per week across meetings, 1:1s, and brainstorming sessions. Needs to quickly capture action items and find past notes by keyword or date. Uses a MacBook at work, iPhone on the go, and occasionally a Windows PC at home.

## 4.2 Maria — The Graduate Student

Role: PhD candidate attending 4–6 lectures and seminars weekly. Records lectures and needs transcriptions and summaries. Organizes notes by course, semester, and topic using folders and tags. Works on a Chromebook and Android phone.

## 4.3 Sam — The Freelance Designer

Role: Manages 5–8 client projects simultaneously. Uses to-do lists and tasks to track deliverables. Needs quick search across project notes and the ability to filter by client tag. Primarily works on an iPad and MacBook.

# 5. Feature Requirements

## 5.1 Note Management (Core)

| ID | Feature | Description | Priority |
| --- | --- | --- | --- |
| F-01 | Create / Edit / Delete notes | WYSIWYG editor with auto-save. Notes support a title and body. | P0 |
| F-02 | Rich-text editing | Bold, italic, strikethrough, bullet lists, numbered lists, headings, code blocks, horizontal rules. | P0 |
| F-03 | Folder organization | Create, rename, move, delete folders. Nested folders up to 3 levels. Drag-and-drop reordering. | P0 |
| F-04 | Tagging system | Add/remove color-coded tags on notes. Auto-suggest existing tags. Bulk tag operations. | P0 |
| F-05 | Search | Full-text search across all notes with instant results. Highlight matches. Recent searches history. | P0 |
| F-06 | Filtering & sorting | Filter by folder, tag, date range, note type. Sort by date created, modified, title, or custom order. | P0 |
| F-07 | To-do lists | Checkbox items within notes. Toggle completion. Progress indicator (X of Y complete). | P0 |
| F-08 | Pinned notes | Pin important notes to the top of any view. | P1 |
| F-09 | Note templates | Pre-built templates (meeting notes, standup, lecture) and custom user templates. | P2 |
| F-10 | Note linking | Link between notes with bidirectional references. Backlinks panel. | P2 |

## 5.2 Task Management

| ID | Feature | Description | Priority |
| --- | --- | --- | --- |
| F-11 | Standalone tasks | Create tasks with title, description, due date, priority (Low/Medium/High/Urgent). | P0 |
| F-12 | Task from note | Convert any to-do item or selected text into a standalone task. Link back to source note. | P1 |
| F-13 | Task views | List view and Kanban board (To Do / In Progress / Done). Filter by priority, due date, or tag. | P1 |
| F-14 | Reminders & notifications | Set reminders for tasks. Push notifications on mobile, system on desktop, browser on web. | P1 |
| F-15 | Recurring tasks | Daily, weekly, monthly, or custom recurrence patterns. | P2 |

## 5.3 Voice & AI Features

| ID | Feature | Description | Priority |
| --- | --- | --- | --- |
| F-16 | Voice-to-text input | Record audio and transcribe to text in real time. Support for 10+ languages. | P1 |
| F-17 | Meeting/lecture recording | Record long-form audio (up to 4 hrs). Store alongside note. Variable speed playback. | P1 |
| F-18 | AI-powered summaries | Auto-generate structured summary (key points, action items, decisions) from transcription. | P1 |
| F-19 | Speaker diarization | Identify and label different speakers in a recording. | P2 |
| F-20 | Smart search in transcripts | Search within transcription text; jump to corresponding audio timestamp. | P2 |

## 5.4 Cross-Platform & Sync

| ID | Feature | Description | Priority |
| --- | --- | --- | --- |
| F-21 | Real-time sync | Changes propagate across all devices within 2 seconds when online. | P0 |
| F-22 | Offline mode | Full read/write offline. Automatic conflict resolution on reconnect (CRDT-based merge). | P0 |
| F-23 | Web app (PWA) | Responsive Progressive Web App accessible via modern browsers. | P0 |
| F-24 | Mobile apps | Native iOS and Android apps with platform-specific UX (share sheet, widgets, haptics). | P0 |
| F-25 | Desktop apps | Native-feeling desktop apps for macOS, Windows, Linux. System tray, global shortcuts. | P1 |

## 5.5 Future Integrations (Post-MVP)

| ID | Feature | Description | Priority |
| --- | --- | --- | --- |
| F-26 | Google Calendar sync | Two-way sync: tasks appear as events; events auto-create note stubs. | P2 |
| F-27 | Slack integration | Save messages as notes. Share notes to channels. Slash command for quick capture. | P2 |
| F-28 | Jira integration | Create Jira tickets from tasks. Bidirectional status sync. Link notes to issues. | P3 |
| F-29 | Microsoft Teams | Bot for capturing meeting notes. Share notes in Teams channels. | P3 |
| F-30 | Zapier / Webhooks | Generic webhook API and Zapier triggers/actions for custom workflows. | P3 |
| F-31 | Import / Export | Import from Evernote, Notion, Apple Notes, Google Keep. Export to MD, PDF, HTML. | P2 |

# 6. MVP Definition

The Minimum Viable Product focuses on delivering a fully functional, cross-platform note-taking experience with core organization and editing capabilities. The MVP should be shippable within 12–14 weeks with a team of 5–7 engineers.

## 6.1 MVP Scope (In)

- Note CRUD with auto-save and rich-text editing (F-01, F-02)

- Folder organization with nesting up to 3 levels (F-03)

- Tagging system with color-coded tags and auto-suggest (F-04)

- Full-text search with instant results (F-05)

- Filtering & sorting by folder, tag, date, and sort order (F-06)

- To-do lists within notes with completion tracking (F-07)

- Standalone tasks with title, due date, and priority (F-11)

- Real-time sync and offline mode with conflict resolution (F-21, F-22)

- Web app (PWA) as the primary launch platform (F-23)

- Mobile apps for iOS and Android (F-24)

- User authentication (email + OAuth with Google/Apple)

## 6.2 MVP Scope (Out)

- Voice transcription and AI summaries (Phase 2)

- Desktop native apps (Phase 2)

- Task Kanban board, recurring tasks, reminders (Phase 2)

- Note templates, note linking (Phase 3)

- All third-party integrations (Phase 3+)

- Speaker diarization, smart transcript search (Phase 3+)

- Team/collaboration features (future consideration)

# 7. Work Breakdown & Task Decomposition

The following decomposition breaks the MVP into epics, each containing discrete engineering tasks with estimated effort in story points (1 SP ≈ 1 ideal engineering day).

## 7.1 Epic 1: Foundation & Infrastructure

| # | Task | Est. (SP) | Deps | Priority |
| --- | --- | --- | --- | --- |
| 1.1 | Project scaffolding (monorepo, CI/CD, linting) | 3 | — | P0 |
| 1.2 | Database schema design (PostgreSQL + content store) | 5 | — | P0 |
| 1.3 | Auth service (email, Google OAuth, Apple Sign-In) | 5 | 1.1 | P0 |
| 1.4 | REST/GraphQL API skeleton with middleware | 5 | 1.1, 1.2 | P0 |
| 1.5 | Real-time sync engine (WebSocket + CRDT/Yjs) | 8 | 1.2, 1.4 | P0 |
| 1.6 | Offline storage (IndexedDB for web, SQLite for mobile) | 5 | 1.2 | P0 |
| 1.7 | File/media upload service (S3, presigned URLs) | 3 | 1.4 | P1 |
| 1.8 | Logging, monitoring, error tracking setup | 2 | 1.1 | P0 |

Epic total: 36 SP

## 7.2 Epic 2: Note Editor & Core UX

| # | Task | Est. (SP) | Deps | Priority |
| --- | --- | --- | --- | --- |
| 2.1 | Rich-text editor component (TipTap/ProseMirror) | 8 | 1.1 | P0 |
| 2.2 | Note CRUD API endpoints | 3 | 1.4 | P0 |
| 2.3 | Auto-save with debounce and conflict detection | 5 | 2.1, 1.5 | P0 |
| 2.4 | To-do / checkbox list plugin for editor | 3 | 2.1 | P0 |
| 2.5 | Note list view (sidebar) with infinite scroll | 3 | 2.2 | P0 |
| 2.6 | Note detail / editor view with responsive layout | 3 | 2.1 | P0 |
| 2.7 | Markdown import/paste support | 2 | 2.1 | P1 |
| 2.8 | Image embed and inline preview | 3 | 2.1, 1.7 | P1 |

Epic total: 30 SP

## 7.3 Epic 3: Organization (Folders, Tags, Search)

| # | Task | Est. (SP) | Deps | Priority |
| --- | --- | --- | --- | --- |
| 3.1 | Folder CRUD API + tree data structure | 3 | 1.4 | P0 |
| 3.2 | Folder UI (tree view, drag-drop, context menu) | 5 | 3.1 | P0 |
| 3.3 | Tag CRUD API + many-to-many relation | 3 | 1.4 | P0 |
| 3.4 | Tag UI (creation, color picker, auto-suggest) | 3 | 3.3 | P0 |
| 3.5 | Full-text search engine (Meilisearch/Typesense) | 5 | 1.2, 2.2 | P0 |
| 3.6 | Search UI (instant results, highlights, history) | 3 | 3.5 | P0 |
| 3.7 | Filter bar (folder, tags, date range, note type) | 3 | 3.1, 3.3 | P0 |
| 3.8 | Sort controls (created, modified, title, custom) | 2 | 2.5 | P0 |

Epic total: 27 SP

## 7.4 Epic 4: Task Management

| # | Task | Est. (SP) | Deps | Priority |
| --- | --- | --- | --- | --- |
| 4.1 | Task data model and CRUD API | 3 | 1.4 | P0 |
| 4.2 | Task list view UI with filters | 3 | 4.1 | P0 |
| 4.3 | Convert note to-do to standalone task | 3 | 4.1, 2.4 | P1 |
| 4.4 | Kanban board view (drag-drop columns) | 5 | 4.1 | P1 |
| 4.5 | Reminder/notification service (push + browser) | 5 | 4.1 | P1 |
| 4.6 | Recurring tasks engine | 3 | 4.1 | P2 |

Epic total: 22 SP

## 7.5 Epic 5: Cross-Platform & Mobile

| # | Task | Est. (SP) | Deps | Priority |
| --- | --- | --- | --- | --- |
| 5.1 | React Native / Flutter project setup | 5 | 1.1 | P0 |
| 5.2 | Mobile note editor (platform-adapted rich text) | 8 | 2.1, 5.1 | P0 |
| 5.3 | Mobile navigation (tab bar, drawer, gestures) | 3 | 5.1 | P0 |
| 5.4 | iOS share sheet extension + widget | 3 | 5.1 | P1 |
| 5.5 | Android share intent + home screen widget | 3 | 5.1 | P1 |
| 5.6 | PWA service worker (offline caching, install) | 3 | 2.1 | P0 |
| 5.7 | Desktop app shell (Tauri) with system tray | 5 | 2.1 | P1 |
| 5.8 | Global keyboard shortcut for quick capture | 2 | 5.7 | P1 |

Epic total: 32 SP

## 7.6 Epic 6: Voice & AI (Phase 2)

| # | Task | Est. (SP) | Deps | Priority |
| --- | --- | --- | --- | --- |
| 6.1 | Audio recording module (Web Audio + native) | 5 | 5.1 | P1 |
| 6.2 | Speech-to-text pipeline (Whisper/Deepgram) | 5 | 6.1, 1.4 | P1 |
| 6.3 | Real-time transcription streaming UI | 5 | 6.2, 2.1 | P1 |
| 6.4 | AI summary generation service (LLM integration) | 5 | 6.2 | P1 |
| 6.5 | Summary editor UI (editable, regenerable) | 3 | 6.4, 2.1 | P1 |
| 6.6 | Speaker diarization pipeline | 8 | 6.2 | P2 |
| 6.7 | Transcript search with audio timestamp linking | 5 | 6.2, 3.5 | P2 |
| 6.8 | Audio playback controls (speed, skip, bookmark) | 3 | 6.1 | P1 |

Epic total: 39 SP

## 7.7 Epic 7: Integrations (Phase 3)

| # | Task | Est. (SP) | Deps | Priority |
| --- | --- | --- | --- | --- |
| 7.1 | Integration framework (OAuth, webhook registry) | 5 | 1.3, 1.4 | P2 |
| 7.2 | Google Calendar two-way sync | 5 | 7.1, 4.1 | P2 |
| 7.3 | Slack bot + slash command | 5 | 7.1 | P2 |
| 7.4 | Jira issue sync (create, status, link) | 5 | 7.1, 4.1 | P3 |
| 7.5 | Microsoft Teams bot | 5 | 7.1 | P3 |
| 7.6 | Zapier / Webhooks public API | 5 | 7.1 | P3 |
| 7.7 | Import engine (Evernote, Notion, Apple Notes) | 8 | 2.2, 3.1 | P2 |
| 7.8 | Export to Markdown, PDF, HTML | 3 | 2.1 | P2 |

Epic total: 41 SP

# 8. Prioritized Roadmap

The roadmap is organized into four phases based on MoSCoW prioritization and dependencies.

## 8.1 Phase 1 — MVP (Weeks 1–14)

Goal: Launch a fully functional cross-platform notes app with core editing, organization, tasks, and sync.

Platforms: Web (PWA) + iOS + Android

Total effort: ~115 SP across Epics 1–5 (P0 tasks)

| Sprint | Focus | Key Deliverables |
| --- | --- | --- |
| Wk 1–2 | Foundation | Monorepo setup, DB schema, auth service, API skeleton |
| Wk 3–4 | Core Editor | Rich-text editor, note CRUD, auto-save, sync engine v1 |
| Wk 5–6 | Organization | Folders, tags, full-text search, filter/sort |
| Wk 7–8 | Tasks + Mobile | Task CRUD, task list view, RN/Flutter project setup |
| Wk 9–10 | Mobile Editor | Mobile note editor, navigation, offline mode |
| Wk 11–12 | Integration Test | Cross-platform sync testing, PWA service worker, bug fixes |
| Wk 13–14 | Polish & Launch | Performance optimization, onboarding flow, beta launch |

## 8.2 Phase 2 — Voice, AI & Enhanced Tasks (Weeks 15–26)

Goal: Add voice transcription, AI summaries, advanced tasks, and desktop apps.

- Voice recording and real-time transcription (F-16, F-17)

- AI-powered meeting/lecture summaries (F-18)

- Kanban board, reminders, notifications (F-13, F-14)

- Task-from-note conversion (F-12)

- Desktop apps for macOS, Windows, Linux (F-25)

- Pinned notes and note templates (F-08, F-09)

## 8.3 Phase 3 — Integrations & Advanced AI (Weeks 27–40)

Goal: Connect NoteFlow to the broader productivity ecosystem.

- Google Calendar and Slack integrations (F-26, F-27)

- Import from Evernote, Notion, Apple Notes, Google Keep (F-31)

- Export to Markdown, PDF, HTML (F-31)

- Speaker diarization and smart transcript search (F-19, F-20)

- Note linking with backlinks (F-10)

## 8.4 Phase 4 — Ecosystem (Weeks 40+)

Goal: Build a platform for automation and team collaboration.

- Jira, Microsoft Teams integrations (F-28, F-29)

- Zapier / Webhooks public API (F-30)

- Team collaboration (shared folders, real-time co-editing)

- Plugin/extension marketplace

# 9. Technical Architecture (Overview)

## 9.1 Tech Stack Recommendations

| Layer | Technology | Rationale |
| --- | --- | --- |
| Frontend (Web) | React + Next.js + TipTap | SSR for SEO; TipTap is extensible and ProseMirror-based |
| Frontend (Mobile) | React Native or Flutter | Cross-platform with shared logic; RN if team knows React |
| Frontend (Desktop) | Tauri (Rust-based) | Lightweight alternative to Electron; smaller binary |
| Backend API | Node.js (Fastify) or Go | High concurrency for real-time sync |
| Database | PostgreSQL + Redis | Structured data in PG; caching and pub/sub in Redis |
| Search | Meilisearch or Typesense | Sub-50ms full-text search; self-hosted |
| Real-time Sync | WebSocket + Yjs (CRDT) | Conflict-free offline sync with strong ecosystem |
| Voice/AI | Whisper API + LLM for summaries | State-of-the-art transcription + structured summaries |
| Storage | S3-compatible (AWS/R2) | Audio files, images, attachments |
| Auth | Supabase Auth or Auth0 | OAuth, JWT, session management out-of-box |
| Infrastructure | Docker + K8s on AWS/GCP | Scalable, reproducible deployments |

## 9.2 Data Model (Simplified)

- User: id, email, name, avatar_url, auth_provider, created_at

- Note: id, user_id, folder_id, title, body (JSON/Yjs doc), is_pinned, created_at, updated_at

- Folder: id, user_id, parent_folder_id, name, sort_order, created_at

- Tag: id, user_id, name, color, created_at

- NoteTag: note_id, tag_id (junction table)

- Task: id, user_id, note_id (optional), title, description, status, priority, due_date, recurrence, created_at, updated_at

- Recording: id, note_id, audio_url, duration, transcript_text, summary_text, created_at

# 10. Non-Functional Requirements

| Category | Requirement |
| --- | --- |
| Performance | Cold start < 1.5s. Note opens < 300ms. Search < 200ms. Sync latency < 2s online. |
| Scalability | Support 100K concurrent users. Horizontal scaling for API and sync layers. |
| Reliability | 99.9% uptime SLA. Zero data loss on sync conflicts (CRDT guarantees). |
| Security | AES-256 at rest, TLS 1.3 in transit. SOC 2 Type II target within 12 months. |
| Privacy | GDPR and CCPA compliant. Data export/deletion on request. No data sold. |
| Accessibility | WCAG 2.1 AA. Screen reader support, keyboard nav, high-contrast mode. |
| Localization | English at launch. i18n framework for 10+ languages by Phase 2. |
| Storage Limits | Free: 100 notes, 500 MB. Pro: unlimited notes, 10 GB. Expandable. |

# 11. Risks & Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| CRDT sync conflicts on complex edits | Medium | Use battle-tested Yjs library. Integration testing with simulated network partitions. |
| Mobile editor performance on old devices | High | Profile on low-end Android early. Lazy-load features. Native fallback. |
| AI transcription accuracy < 90% | Medium | Manual correction UI. Allow provider choice. Fine-tune summary prompts. |
| Competitive pressure (Notion, Obsidian) | High | Focus on speed and simplicity. Ship fast, iterate on feedback. Avoid bloat. |
| Scope creep in MVP | High | Strict MVP scope (Section 6). Weekly scope review. Features go to backlog. |
| Platform-specific bugs | Medium | Shared test suite with platform-specific CI. Beta testing with device diversity. |

# 12. Open Questions

- React Native vs Flutter for mobile? Decision needed by Week 1.

- Pricing model for AI/voice features? Per-minute transcription adds cost. Need usage-based or tiered pricing analysis.

- Real-time collaboration (multi-user editing) in MVP or defer to Phase 4?

- Which AI provider for summaries? Evaluate cost, quality, and structured output capabilities.

- End-to-end encryption: desirable for privacy, but blocks server-side search and AI features. Optional mode?

# 13. Appendix

## 13.1 Priority Definitions

| Level | Label | Definition |
| --- | --- | --- |
| P0 | Must Have (MVP) | Core functionality required for launch. Product is unusable without it. |
| P1 | Should Have | Important for satisfaction but not blocking launch. Target for Phase 2. |
| P2 | Nice to Have | Enhances the product. Planned for Phase 3 or deferred based on feedback. |
| P3 | Future | Long-term roadmap items. Dependent on market validation and resources. |

## 13.2 Story Point Summary

| Epic | Story Points | Phase |
| --- | --- | --- |
| Epic 1: Foundation & Infrastructure | 36 | Phase 1 |
| Epic 2: Note Editor & Core UX | 30 | Phase 1 |
| Epic 3: Organization (Folders, Tags, Search) | 27 | Phase 1 |
| Epic 4: Task Management | 22 | Phase 1–2 |
| Epic 5: Cross-Platform & Mobile | 32 | Phase 1–2 |
| Epic 6: Voice & AI | 39 | Phase 2 |
| Epic 7: Integrations | 41 | Phase 3 |
| TOTAL | 227 SP | — |

End of document.